## KPI Summary
report_date | total_tasks | sla_breached | at_risk | on_track | data_errors | compliance_rate | highest_breach_svc
2026-05-01 | 60 | 24 | 11 | 25 | 0 | 41.7% | Report Generation

## By Service
service_id | service_name | sla_hours | total_tasks | breached_tasks | avg_actual_tat | max_actual_tat | compliance_pct
SVC-001 | Data Ingestion | 2 | 10 | 5 | 1.85 | 2.85 | 50
SVC-002 | Report Generation | 4 | 10 | 6 | 4.11 | 6.64 | 40
SVC-003 | Reconciliation | 6 | 10 | 3 | 4.67 | 10.7 | 70
SVC-004 | Client Delivery | 3 | 10 | 3 | 2.23 | 4.83 | 70
SVC-005 | Audit Validation | 8 | 10 | 4 | 7.38 | 13.08 | 60
SVC-006 | Data Transformation | 5 | 10 | 3 | 4.42 | 6.6 | 70

## By Team
team | total_tasks | breached_tasks | avg_actual_tat | compliance_pct
Gamma | 20 | 6 | 4.54 | 70
Alpha | 20 | 8 | 2.04 | 60
Beta | 20 | 10 | 5.74 | 50

## By Owner
owner | team | total_tasks | breached_tasks | compliance_pct
Divya R. | Gamma | 8 | 1 | 87.5
Priya S. | Alpha | 7 | 2 | 71.4
Nikhil V. | Gamma | 6 | 2 | 66.7
Kiran L. | Beta | 10 | 4 | 60
Meera K. | Alpha | 9 | 4 | 55.6
Arjun M. | Alpha | 4 | 2 | 50
Lakshmi J. | Gamma | 6 | 3 | 50
Ravi T. | Beta | 7 | 4 | 42.9
Sneha P. | Beta | 3 | 2 | 33.3

## Breach Alerts
task_id | service_name | priority | team | owner | actual_tat_hrs | sla_hours | tat_variance_hrs | tat_variance_pct | sla_status | start_time | end_time
TSK-0032 | Reconciliation | P2 | Gamma | Divya R. | 10.7 | 6 | 4.7 | 78.3 | SLA Breached | 2026-04-28 17:00 | 2026-04-29 03:42
TSK-0007 | Report Generation | P1 | Beta | Ravi T. | 6.64 | 4 | 2.64 | 66 | SLA Breached | 2026-04-25 10:00 | 2026-04-25 16:38
TSK-0004 | Audit Validation | P2 | Beta | Ravi T. | 13.08 | 8 | 5.08 | 63.5 | SLA Breached | 2026-04-29 18:00 | 2026-04-30 07:05
TSK-0021 | Client Delivery | P1 | Alpha | Meera K. | 4.83 | 3 | 1.83 | 61 | SLA Breached | 2026-04-26 17:00 | 2026-04-26 21:50
TSK-0048 | Data Ingestion | P1 | Alpha | Arjun M. | 2.85 | 2 | 0.85 | 42.5 | SLA Breached | 2026-04-25 09:00 | 2026-04-25 11:51
TSK-0055 | Report Generation | P1 | Beta | Sneha P. | 5.66 | 4 | 1.66 | 41.5 | SLA Breached | 2026-04-28 07:00 | 2026-04-28 12:40
TSK-0060 | Data Ingestion | P1 | Alpha | Arjun M. | 2.78 | 2 | 0.78 | 39 | SLA Breached | 2026-04-24 18:00 | 2026-04-24 20:47
TSK-0056 | Reconciliation | P2 | Gamma | Lakshmi J. | 8.21 | 6 | 2.21 | 36.8 | SLA Breached | 2026-04-29 08:00 | 2026-04-29 16:13
TSK-0035 | Data Transformation | P2 | Gamma | Nikhil V. | 6.6 | 5 | 1.6 | 32 | SLA Breached | 2026-04-26 17:00 | 2026-04-26 23:36
TSK-0008 | Reconciliation | P2 | Gamma | Lakshmi J. | 7.77 | 6 | 1.77 | 29.5 | SLA Breached | 2026-04-28 07:00 | 2026-04-28 14:46
TSK-0041 | Data Transformation | P2 | Gamma | Lakshmi J. | 6.41 | 5 | 1.41 | 28.2 | SLA Breached | 2026-04-26 10:00 | 2026-04-26 16:25
TSK-0003 | Client Delivery | P1 | Alpha | Priya S. | 3.72 | 3 | 0.72 | 24 | SLA Breached | 2026-04-25 18:00 | 2026-04-25 21:43
TSK-0054 | Data Ingestion | P1 | Alpha | Meera K. | 2.45 | 2 | 0.45 | 22.5 | SLA Breached | 2026-04-27 15:00 | 2026-04-27 17:27
TSK-0010 | Audit Validation | P2 | Beta | Kiran L. | 9.55 | 8 | 1.55 | 19.4 | SLA Breached | 2026-04-29 15:00 | 2026-04-30 00:33
TSK-0001 | Report Generation | P1 | Beta | Kiran L. | 4.69 | 4 | 0.69 | 17.2 | SLA Breached | 2026-04-24 07:00 | 2026-04-24 11:41
TSK-0028 | Audit Validation | P2 | Beta | Sneha P. | 8.95 | 8 | 0.95 | 11.9 | SLA Breached | 2026-04-29 12:00 | 2026-04-29 20:57
TSK-0049 | Report Generation | P1 | Beta | Kiran L. | 4.42 | 4 | 0.42 | 10.5 | SLA Breached | 2026-04-27 08:00 | 2026-04-27 12:25
TSK-0059 | Data Transformation | P2 | Gamma | Nikhil V. | 5.5 | 5 | 0.5 | 10 | SLA Breached | 2026-04-27 09:00 | 2026-04-27 14:30
TSK-0051 | Client Delivery | P1 | Alpha | Priya S. | 3.29 | 3 | 0.29 | 9.7 | SLA Breached | 2026-04-29 09:00 | 2026-04-29 12:17
TSK-0018 | Data Ingestion | P1 | Alpha | Meera K. | 2.18 | 2 | 0.18 | 9 | SLA Breached | 2026-04-26 07:00 | 2026-04-26 09:11
TSK-0013 | Report Generation | P1 | Beta | Ravi T. | 4.24 | 4 | 0.24 | 6 | SLA Breached | 2026-04-29 13:00 | 2026-04-29 17:14
TSK-0037 | Report Generation | P1 | Beta | Kiran L. | 4.18 | 4 | 0.18 | 4.5 | SLA Breached | 2026-04-26 07:00 | 2026-04-26 11:11
TSK-0040 | Audit Validation | P2 | Beta | Ravi T. | 8.31 | 8 | 0.31 | 3.9 | SLA Breached | 2026-04-25 16:00 | 2026-04-26 00:19
TSK-0042 | Data Ingestion | P1 | Alpha | Meera K. | 2.05 | 2 | 0.05 | 2.5 | SLA Breached | 2026-04-27 13:00 | 2026-04-27 15:03

## Trend Analysis
service_id | service_name | task_date | actual_tat_hrs | rolling_avg_tat
SVC-001 | Data Ingestion | 2026-04-24 | 1.6967 | 1.7
SVC-001 | Data Ingestion | 2026-04-25 | 2.85 | 2.27
SVC-001 | Data Ingestion | 2026-04-26 | 1.83 | 2.13
SVC-001 | Data Ingestion | 2026-04-27 | 2.25 | 2.16
SVC-001 | Data Ingestion | 2026-04-28 | 0.8 | 1.89
SVC-001 | Data Ingestion | 2026-04-29 | 1.64 | 1.84
SVC-002 | Report Generation | 2026-04-24 | 4.69 | 4.69
SVC-002 | Report Generation | 2026-04-25 | 6.64 | 5.66
SVC-002 | Report Generation | 2026-04-26 | 4.18 | 5.17
SVC-002 | Report Generation | 2026-04-27 | 3.3933 | 4.73
SVC-002 | Report Generation | 2026-04-28 | 5.66 | 4.91
SVC-002 | Report Generation | 2026-04-29 | 3.48 | 4.67
SVC-002 | Report Generation | 2026-04-30 | 2.82 | 4.41
SVC-003 | Reconciliation | 2026-04-25 | 4.89 | 4.89
SVC-003 | Reconciliation | 2026-04-26 | 2.93 | 3.91
SVC-003 | Reconciliation | 2026-04-27 | 1.89 | 3.24
SVC-003 | Reconciliation | 2026-04-28 | 9.235 | 4.74
SVC-003 | Reconciliation | 2026-04-29 | 8.21 | 5.43
SVC-003 | Reconciliation | 2026-04-30 | 2.45 | 4.93
SVC-004 | Client Delivery | 2026-04-25 | 2.97 | 2.97
SVC-004 | Client Delivery | 2026-04-26 | 4.83 | 3.9
SVC-004 | Client Delivery | 2026-04-27 | 1.18 | 2.99
SVC-004 | Client Delivery | 2026-04-28 | 1.8 | 2.7
SVC-004 | Client Delivery | 2026-04-29 | 3.29 | 2.81
SVC-004 | Client Delivery | 2026-04-30 | 0.52 | 2.43
SVC-005 | Audit Validation | 2026-04-24 | 5.58 | 5.58
SVC-005 | Audit Validation | 2026-04-25 | 6.05 | 5.82
SVC-005 | Audit Validation | 2026-04-26 | 6.49 | 6.04
SVC-005 | Audit Validation | 2026-04-27 | 6.21 | 6.08
SVC-005 | Audit Validation | 2026-04-29 | 9.1475 | 6.7
SVC-005 | Audit Validation | 2026-04-30 | 6.79 | 6.71
SVC-006 | Data Transformation | 2026-04-24 | 4.22 | 4.22
SVC-006 | Data Transformation | 2026-04-25 | 4.305 | 4.26
SVC-006 | Data Transformation | 2026-04-26 | 4.72 | 4.42
SVC-006 | Data Transformation | 2026-04-27 | 4.365 | 4.4
SVC-006 | Data Transformation | 2026-04-28 | 3.71 | 4.26

## Full Log
task_id | service_id | owner | start_time | end_time | actual_tat_hrs | service_name | sla_hours | priority | team | tat_variance_hrs | tat_variance_pct | utilisation_ratio | sla_status | is_breach
TSK-0001 | SVC-002 | Kiran L. | 2026-04-24 07:00 | 2026-04-24 11:41 | 4.69 | Report Generation | 4 | P1 | Beta | 0.69 | 17.2 | 1.172 | SLA Breached | TRUE
TSK-0002 | SVC-003 | Lakshmi J. | 2026-04-26 10:00 | 2026-04-26 15:20 | 5.33 | Reconciliation | 6 | P2 | Gamma | -0.67 | -11.2 | 0.888 | At Risk | FALSE
TSK-0003 | SVC-004 | Priya S. | 2026-04-25 18:00 | 2026-04-25 21:43 | 3.72 | Client Delivery | 3 | P1 | Alpha | 0.72 | 24 | 1.24 | SLA Breached | TRUE
TSK-0004 | SVC-005 | Ravi T. | 2026-04-29 18:00 | 2026-04-30 07:05 | 13.08 | Audit Validation | 8 | P2 | Beta | 5.08 | 63.5 | 1.635 | SLA Breached | TRUE
TSK-0005 | SVC-006 | Lakshmi J. | 2026-04-24 16:00 | 2026-04-24 20:13 | 4.22 | Data Transformation | 5 | P2 | Gamma | -0.78 | -15.6 | 0.844 | At Risk | FALSE
TSK-0006 | SVC-001 | Arjun M. | 2026-04-24 07:00 | 2026-04-24 08:41 | 1.69 | Data Ingestion | 2 | P1 | Alpha | -0.31 | -15.5 | 0.845 | At Risk | FALSE
TSK-0007 | SVC-002 | Ravi T. | 2026-04-25 10:00 | 2026-04-25 16:38 | 6.64 | Report Generation | 4 | P1 | Beta | 2.64 | 66 | 1.66 | SLA Breached | TRUE
TSK-0008 | SVC-003 | Lakshmi J. | 2026-04-28 07:00 | 2026-04-28 14:46 | 7.77 | Reconciliation | 6 | P2 | Gamma | 1.77 | 29.5 | 1.295 | SLA Breached | TRUE
TSK-0009 | SVC-004 | Meera K. | 2026-04-25 18:00 | 2026-04-25 20:13 | 2.22 | Client Delivery | 3 | P1 | Alpha | -0.78 | -26 | 0.74 | On Track | FALSE
TSK-0010 | SVC-005 | Kiran L. | 2026-04-29 15:00 | 2026-04-30 00:33 | 9.55 | Audit Validation | 8 | P2 | Beta | 1.55 | 19.4 | 1.194 | SLA Breached | TRUE
TSK-0011 | SVC-006 | Nikhil V. | 2026-04-25 14:00 | 2026-04-25 17:43 | 3.71 | Data Transformation | 5 | P2 | Gamma | -1.29 | -25.8 | 0.742 | On Track | FALSE
TSK-0012 | SVC-001 | Meera K. | 2026-04-26 07:00 | 2026-04-26 08:29 | 1.48 | Data Ingestion | 2 | P1 | Alpha | -0.52 | -26 | 0.74 | On Track | FALSE
TSK-0013 | SVC-002 | Ravi T. | 2026-04-29 13:00 | 2026-04-29 17:14 | 4.24 | Report Generation | 4 | P1 | Beta | 0.24 | 6 | 1.06 | SLA Breached | TRUE
TSK-0014 | SVC-003 | Nikhil V. | 2026-04-26 09:00 | 2026-04-26 09:32 | 0.53 | Reconciliation | 6 | P2 | Gamma | -5.47 | -91.2 | 0.088 | On Track | FALSE
TSK-0015 | SVC-004 | Priya S. | 2026-04-30 12:00 | 2026-04-30 12:31 | 0.52 | Client Delivery | 3 | P1 | Alpha | -2.48 | -82.7 | 0.173 | On Track | FALSE
TSK-0016 | SVC-005 | Ravi T. | 2026-04-24 13:00 | 2026-04-24 18:35 | 5.58 | Audit Validation | 8 | P2 | Beta | -2.42 | -30.2 | 0.698 | On Track | FALSE
TSK-0017 | SVC-006 | Divya R. | 2026-04-26 12:00 | 2026-04-26 14:28 | 2.47 | Data Transformation | 5 | P2 | Gamma | -2.53 | -50.6 | 0.494 | On Track | FALSE
TSK-0018 | SVC-001 | Meera K. | 2026-04-26 07:00 | 2026-04-26 09:11 | 2.18 | Data Ingestion | 2 | P1 | Alpha | 0.18 | 9 | 1.09 | SLA Breached | TRUE
TSK-0019 | SVC-002 | Kiran L. | 2026-04-27 15:00 | 2026-04-27 17:10 | 2.17 | Report Generation | 4 | P1 | Beta | -1.83 | -45.8 | 0.542 | On Track | FALSE
TSK-0020 | SVC-003 | Divya R. | 2026-04-27 08:00 | 2026-04-27 09:53 | 1.89 | Reconciliation | 6 | P2 | Gamma | -4.11 | -68.5 | 0.315 | On Track | FALSE
TSK-0021 | SVC-004 | Meera K. | 2026-04-26 17:00 | 2026-04-26 21:50 | 4.83 | Client Delivery | 3 | P1 | Alpha | 1.83 | 61 | 1.61 | SLA Breached | TRUE
TSK-0022 | SVC-005 | Kiran L. | 2026-04-30 12:00 | 2026-04-30 18:47 | 6.79 | Audit Validation | 8 | P2 | Beta | -1.21 | -15.1 | 0.849 | At Risk | FALSE
TSK-0023 | SVC-006 | Lakshmi J. | 2026-04-25 18:00 | 2026-04-25 22:54 | 4.9 | Data Transformation | 5 | P2 | Gamma | -0.1 | -2 | 0.98 | At Risk | FALSE
TSK-0024 | SVC-001 | Priya S. | 2026-04-24 17:00 | 2026-04-24 17:37 | 0.62 | Data Ingestion | 2 | P1 | Alpha | -1.38 | -69 | 0.31 | On Track | FALSE
TSK-0025 | SVC-002 | Ravi T. | 2026-04-30 11:00 | 2026-04-30 13:49 | 2.82 | Report Generation | 4 | P1 | Beta | -1.18 | -29.5 | 0.705 | On Track | FALSE
TSK-0026 | SVC-003 | Divya R. | 2026-04-30 10:00 | 2026-04-30 16:00 | 6 | Reconciliation | 6 | P2 | Gamma | 0 | 0 | 1 | At Risk | FALSE
TSK-0027 | SVC-004 | Priya S. | 2026-04-27 11:00 | 2026-04-27 12:18 | 1.3 | Client Delivery | 3 | P1 | Alpha | -1.7 | -56.7 | 0.433 | On Track | FALSE
TSK-0028 | SVC-005 | Sneha P. | 2026-04-29 12:00 | 2026-04-29 20:57 | 8.95 | Audit Validation | 8 | P2 | Beta | 0.95 | 11.9 | 1.119 | SLA Breached | TRUE
TSK-0029 | SVC-006 | Divya R. | 2026-04-26 12:00 | 2026-04-26 15:24 | 3.4 | Data Transformation | 5 | P2 | Gamma | -1.6 | -32 | 0.68 | On Track | FALSE
TSK-0030 | SVC-001 | Priya S. | 2026-04-29 11:00 | 2026-04-29 12:38 | 1.64 | Data Ingestion | 2 | P1 | Alpha | -0.36 | -18 | 0.82 | At Risk | FALSE
TSK-0031 | SVC-002 | Kiran L. | 2026-04-29 17:00 | 2026-04-29 19:43 | 2.72 | Report Generation | 4 | P1 | Beta | -1.28 | -32 | 0.68 | On Track | FALSE
TSK-0032 | SVC-003 | Divya R. | 2026-04-28 17:00 | 2026-04-29 03:42 | 10.7 | Reconciliation | 6 | P2 | Gamma | 4.7 | 78.3 | 1.783 | SLA Breached | TRUE
TSK-0033 | SVC-004 | Priya S. | 2026-04-28 18:00 | 2026-04-28 20:50 | 2.83 | Client Delivery | 3 | P1 | Alpha | -0.17 | -5.7 | 0.943 | At Risk | FALSE
TSK-0034 | SVC-005 | Ravi T. | 2026-04-25 14:00 | 2026-04-25 17:47 | 3.79 | Audit Validation | 8 | P2 | Beta | -4.21 | -52.6 | 0.474 | On Track | FALSE
TSK-0035 | SVC-006 | Nikhil V. | 2026-04-26 17:00 | 2026-04-26 23:36 | 6.6 | Data Transformation | 5 | P2 | Gamma | 1.6 | 32 | 1.32 | SLA Breached | TRUE
TSK-0036 | SVC-001 | Meera K. | 2026-04-28 10:00 | 2026-04-28 10:48 | 0.8 | Data Ingestion | 2 | P1 | Alpha | -1.2 | -60 | 0.4 | On Track | FALSE
TSK-0037 | SVC-002 | Kiran L. | 2026-04-26 07:00 | 2026-04-26 11:11 | 4.18 | Report Generation | 4 | P1 | Beta | 0.18 | 4.5 | 1.045 | SLA Breached | TRUE
TSK-0038 | SVC-003 | Divya R. | 2026-04-30 07:00 | 2026-04-30 07:25 | 0.41 | Reconciliation | 6 | P2 | Gamma | -5.59 | -93.2 | 0.068 | On Track | FALSE
TSK-0039 | SVC-004 | Arjun M. | 2026-04-27 11:00 | 2026-04-27 12:04 | 1.06 | Client Delivery | 3 | P1 | Alpha | -1.94 | -64.7 | 0.353 | On Track | FALSE
TSK-0040 | SVC-005 | Ravi T. | 2026-04-25 16:00 | 2026-04-26 00:19 | 8.31 | Audit Validation | 8 | P2 | Beta | 0.31 | 3.9 | 1.039 | SLA Breached | TRUE
TSK-0041 | SVC-006 | Lakshmi J. | 2026-04-26 10:00 | 2026-04-26 16:25 | 6.41 | Data Transformation | 5 | P2 | Gamma | 1.41 | 28.2 | 1.282 | SLA Breached | TRUE
TSK-0042 | SVC-001 | Meera K. | 2026-04-27 13:00 | 2026-04-27 15:03 | 2.05 | Data Ingestion | 2 | P1 | Alpha | 0.05 | 2.5 | 1.025 | SLA Breached | TRUE
TSK-0043 | SVC-002 | Kiran L. | 2026-04-27 09:00 | 2026-04-27 12:35 | 3.59 | Report Generation | 4 | P1 | Beta | -0.41 | -10.2 | 0.898 | At Risk | FALSE
TSK-0044 | SVC-003 | Nikhil V. | 2026-04-25 10:00 | 2026-04-25 14:53 | 4.89 | Reconciliation | 6 | P2 | Gamma | -1.11 | -18.5 | 0.815 | At Risk | FALSE
TSK-0045 | SVC-004 | Meera K. | 2026-04-28 15:00 | 2026-04-28 15:51 | 0.85 | Client Delivery | 3 | P1 | Alpha | -2.15 | -71.7 | 0.283 | On Track | FALSE
TSK-0046 | SVC-005 | Sneha P. | 2026-04-29 16:00 | 2026-04-29 21:01 | 5.01 | Audit Validation | 8 | P2 | Beta | -2.99 | -37.4 | 0.626 | On Track | FALSE
TSK-0047 | SVC-006 | Nikhil V. | 2026-04-28 13:00 | 2026-04-28 16:43 | 3.71 | Data Transformation | 5 | P2 | Gamma | -1.29 | -25.8 | 0.742 | On Track | FALSE
TSK-0048 | SVC-001 | Arjun M. | 2026-04-25 09:00 | 2026-04-25 11:51 | 2.85 | Data Ingestion | 2 | P1 | Alpha | 0.85 | 42.5 | 1.425 | SLA Breached | TRUE
TSK-0049 | SVC-002 | Kiran L. | 2026-04-27 08:00 | 2026-04-27 12:25 | 4.42 | Report Generation | 4 | P1 | Beta | 0.42 | 10.5 | 1.105 | SLA Breached | TRUE
TSK-0050 | SVC-003 | Divya R. | 2026-04-30 08:00 | 2026-04-30 08:56 | 0.94 | Reconciliation | 6 | P2 | Gamma | -5.06 | -84.3 | 0.157 | On Track | FALSE
TSK-0051 | SVC-004 | Priya S. | 2026-04-29 09:00 | 2026-04-29 12:17 | 3.29 | Client Delivery | 3 | P1 | Alpha | 0.29 | 9.7 | 1.097 | SLA Breached | TRUE
TSK-0052 | SVC-005 | Kiran L. | 2026-04-27 16:00 | 2026-04-27 22:13 | 6.21 | Audit Validation | 8 | P2 | Beta | -1.79 | -22.4 | 0.776 | On Track | FALSE
TSK-0053 | SVC-006 | Divya R. | 2026-04-27 13:00 | 2026-04-27 16:14 | 3.23 | Data Transformation | 5 | P2 | Gamma | -1.77 | -35.4 | 0.646 | On Track | FALSE
TSK-0054 | SVC-001 | Meera K. | 2026-04-27 15:00 | 2026-04-27 17:27 | 2.45 | Data Ingestion | 2 | P1 | Alpha | 0.45 | 22.5 | 1.225 | SLA Breached | TRUE
TSK-0055 | SVC-002 | Sneha P. | 2026-04-28 07:00 | 2026-04-28 12:40 | 5.66 | Report Generation | 4 | P1 | Beta | 1.66 | 41.5 | 1.415 | SLA Breached | TRUE
TSK-0056 | SVC-003 | Lakshmi J. | 2026-04-29 08:00 | 2026-04-29 16:13 | 8.21 | Reconciliation | 6 | P2 | Gamma | 2.21 | 36.8 | 1.368 | SLA Breached | TRUE
TSK-0057 | SVC-004 | Meera K. | 2026-04-28 11:00 | 2026-04-28 12:43 | 1.72 | Client Delivery | 3 | P1 | Alpha | -1.28 | -42.7 | 0.573 | On Track | FALSE
TSK-0058 | SVC-005 | Kiran L. | 2026-04-26 08:00 | 2026-04-26 14:29 | 6.49 | Audit Validation | 8 | P2 | Beta | -1.51 | -18.9 | 0.811 | At Risk | FALSE
TSK-0059 | SVC-006 | Nikhil V. | 2026-04-27 09:00 | 2026-04-27 14:30 | 5.5 | Data Transformation | 5 | P2 | Gamma | 0.5 | 10 | 1.1 | SLA Breached | TRUE
TSK-0060 | SVC-001 | Arjun M. | 2026-04-24 18:00 | 2026-04-24 20:47 | 2.78 | Data Ingestion | 2 | P1 | Alpha | 0.78 | 39 | 1.39 | SLA Breached | TRUE